## process list
Project Number
Activity | Requested Date | Actual Date | Dept | Engineer | Notes/Comments | Status |  |  |  | Q | D | C | F | TOTAL
[6 empty] | Yes | No | Late | Inadequate
[6 empty] | 100 | 0 | 50 | 30
Program Definition
Quality Function Deployment activities | [9 empty] | 75 |  |  | 25 | 0
Preliminary Engineering Bill of Materials | [9 empty] | 25 |  |  | 75 | 0
Propduct Specifications | [11 empty] | 25 | 75 | 0
Specification Reviews | [9 empty] | 75 |  |  | 25 | 0
Establish Quality and Reliability Targets | [9 empty] | 100 |  |  |  | 0
Product Assurance Plan | [9 empty] | 100 |  |  |  | 0
Prelminary manufacturing Bill of Materials | [10 empty] | 50 |  | 50 | 0
Prelimiinary Process Flow Diagram | [9 empty] | 25 | 75 |  |  | 0
Special Process Characteristics | [9 empty] | 75 | 25 |  |  | 0
Software Quality Assurance plan | [9 empty] | 75 |  |  | 25 | 0
0
Product Development
DFMEA | [9 empty] | 75 |  |  | 25 | 0
DFMA | [9 empty] | 50 |  | 25 | 25 | 0
Key Product Characteristics Identified | [9 empty] | 50 |  |  | 50 | 0
Design Verification Testing | [9 empty] | 75 |  |  | 25 | 0
New Equipment and Tooling Requirements | [9 empty] | 50 | 50 |  |  | 0
Gauges R&R | [9 empty] | 50 |  |  |  | 0
Product test equipment | [9 empty] | 75 |  |  | 25 | 0
Engineering Bill of Materials released | [9 empty] | 75 |  |  | 25 | 0
| QDCF Sum For Next Gate | [12 empty] | 0
Process Development
PFMEA | [9 empty] | 75 | 25 |  |  | 0
Key Control Characteristics | [9 empty] | 100 |  |  |  | 0
Process Control Plan | [9 empty] | 75 |  |  | 25 | 0
Special Process Characteristics | [13 empty] | 0
Process Flow | [9 empty] | 50 | 50 |  |  | 0
Process Floor Plan | [9 empty] | 50 |  | 50 |  | 0
Pre-Launch Control Plan | [9 empty] | 75 | 25 |  |  | 0
Process Instructions | [9 empty] | 100 |  |  |  | 0
Process Verification | [9 empty] | 75 |  |  | 25 | 0
Product and Process Quality System Review | [9 empty] | 100 |  |  |  | 0
Measurment Systems Analysis | [13 empty] | 0
Packaging specification | [9 empty] | 50 |  |  |  | 0
Packaging specification review | [9 empty] | 75 | 25 |  |  | 0
Process Capability Study | [9 empty] | 100 |  |  |  | 0
EDI | [11 empty] | 25 | 75 | 0
| QDCF Sum For Next Gate | [12 empty] | 0
Validation of Product and Process
Design Validation Plan and Report (DVP&R) | [9 empty] | 75 |  |  | 25 | 0
Preliminary Process Capability | [12 empty] | 100 | 0
Bench Testing | [12 empty] | 100 | 0
Systems testing | [12 empty] | 100 | 0
Measurment Systems Evaluation | [9 empty] | 100 |  |  |  | 0
Production Part Approval | [12 empty] | 100 | 0
Packaging Evaluation | [12 empty] | 100 | 0
Production Control Plan | [9 empty] | 50 | 50 |  |  | 0
| QDCF Sum For Next Gate | [12 empty] | 0
Release to Production
Process Sign off | [9 empty] | 100 |  |  |  | 0
Trial Production Run | [10 empty] | 50 |  | 50 | 0
Pilot Runs | [9 empty] | 100 |  |  |  | 0
Run at Rate | [9 empty] | 50 | 50 |  |  | 0
Production test Equipment evaluation | [9 empty] | 75 | 25 |  |  | 0
Design Change Notification | [9 empty] | 50 |  |  | 50 | 0
| QDCF Sum For Next Gate | [12 empty] | 0
[9 empty] | Weighted Value |  |  |  |  | 0

## QDCF
Initial | Definition
Quality | Able to deliver the project and project deliverables (product) at the quality levels comitted to, and expected by the customer. This goes for hardware features as well as software functionality meeting those customer expectations
Delivery | Timely delivery of the project deliverables. This is not restricted to the product of the project but includes ancillary deliverables such as documentation and other support deliverables
Cost | The cost for the project and the product are within comitments by PD and the expecations of the customer for the project.
Features | The feature content of the product meets that comitted to by product development and expected by the customer. This means the quantity of functions as well as performance of the individual functions meeting customer expectations
**Expectation management